## Read_Me
Kerala Home, Phase 1: schedules
Site: Guntur, Andhra Pradesh (agricultural land: conversion to be confirmed). Stage: Draft for professional review. Revision B (pre-construction draft), 30 Oct 2026.
Dimensions in feet. Centreline sizes match the plan grid; clear sizes are wall face to wall face after plaster.
How to use
Yellow cells are for you to fill in (budget estimates, chosen products, status). Everything else is calculated or drawn from the plan.
Example: in Furniture, type 18000 in 'Est. unit cost (Rs)' for an item costing Rs 18,000; the line total and grand total update automatically.
Areas, heights and totals are formulas, so editing a room's size updates its area.
Tabs
Rooms: room sizes and areas. Doors / Windows: opening sizes and types. Furniture: every furniture item, fixture and built-in, with budget columns.
Finishes: floor, wall and ceiling finishes. Specification: materials and why (Guntur conditions). Quantities: take-off for pricing, with rate cells.
Electrical / Plumbing: every point with room and height. Checklist: room-by-room mistakes to avoid, with a status column. Hold_Points: inspections before work is covered.
Open_Issues: items to resolve with professionals. Decisions: what has been agreed so far.

## Rooms
ID | Room | Zone | E-W (ft) | N-S (ft) | Area (sq ft) | Area (sq m) | Clear E-W (ft) | Clear N-S (ft) | Clear area (sq ft) | Floor level | Ceiling | Notes
R01 | Workstation (open, walls optional later) | Master suite | 9 | 8 |  |  | 8.62 | 7.62 |  | +2'-0" | Flat 9'-6"
R02 | Master bay (old store, open to the bedroom) | Master suite | 7 | 8 |  |  | 6.79 | 7.62 |  | +2'-0" | Flat 9'-6"
R03 | Dressing alcove | Master suite | 6.5 | 6 |  |  | 6.12 | 5.71 |  | +2'-0" | Flat 9'-6"
R04 | Ensuite | Master suite | 6.5 | 8 |  |  | 5.92 | 7.33 |  | +1'-11.5" | Flat 8'-6" | Widened 1'-6" into the master: WC, 3'-6" vanity, walk-in shower
R05 | Master bedroom | Master suite | 9.5 | 14 |  |  | 9.08 | 13.62 |  | +2'-0" | Flat 9'-6"
R08 | Bath 2 (attached to Bedroom 2) | Private | 7 | 7 |  |  | 6.5 | 6.33 |  | +1'-11.5" | Flat 8'-6"
R07 | Common bath | Service | 6.5 | 6 |  |  | 6 | 5.42 |  | +1'-11.5" | Flat 8'-6"
R09 | Bedroom 2 | Private | 17 | 14.5 |  |  | 16.58 | 13.91 |  | +2'-0" | Flat 9'-6" | Includes 2' x 6' built-in wardrobe
R10 | Dining | Living | 11 | 8 |  |  | 10.79 | 8 |  | +2'-0" | Sloped (open to ventilator) | Under the ventilator lantern, at plot centre
R19 | Dining bay (north window) | Living | 11 | 6 |  |  | 10.79 | 5.62 |  | +2'-0" | Sloped (follows roof)
R13 | Wet area (open to the walkway) | Service | 5 | 6 |  |  | 4.5 | 5.71 |  | +1'-9" | Sloped (open truss) | Semi-open, jali on south wall
R14 | Sitting and serving area (open) | Living | 20.5 | 7.5 |  |  | 20.08 | 6.92 |  | +2'-0" | Flat 9'-6"
R15 | Kitchen | Service | 14 | 10 |  |  | 13.41 | 9.25 |  | +2'-0" | Flat 9'-6"
R16 | Living | Living | 12 | 12 |  |  | 11.62 | 11.25 |  | +2'-0" | Sloped (follows roof)
R11 | Pooja | Living | 4 | 4 |  |  | 3.42 | 3.42 |  | +2'-3" | Flat 9'-6"
R17 | Poomukham (verandah) | Entry | 6 | 12 |  |  | 5.62 | 11.62 |  | +1'-6" | Sloped (exposed rafters) | Open verandah
| Total | [10 empty] | Built footprint 62' x 22' = 1,364 sq ft
Note on G1: 1 sq ft = 0.092903 sq m

## Doors
ID | Location | Width (ft) | Height (ft) | Operation | Type / material | Vent above (7'-6" to 9'-0") | Chosen product | Status
D01 | Main entrance | 3 | 7 | Hinged, double | Teak panelled, double leaf | -
D05 | Ensuite (opens outward) | 2.5 | 7 | Hinged, single | Flush, waterproof (WPC/FRP) | -
D06 | Master suite entry, from the sitting area into the master bay | 2.5 | 7 | Hinged, single | Teak panelled, single leaf | -
D10 | Bedroom 2 (from the sitting area, east end) | 3 | 7 | Hinged, single | Flush, teak veneer | -
D15 | Common bath (from the sitting area, opens outward, hinged at the north jamb so the open leaf stays clear of the counter) | 2.5 | 7 | Hinged, single | Flush, waterproof (WPC/FRP), door closer | -
D16 | Bath 2 (east wall, from Bedroom 2, opens outward) | 2.5 | 7 | Hinged, single | Flush, waterproof (WPC/FRP) | -
D11 | Pooja | 3 | 7 | Hinged, double | Carved teak, double leaf (opens inward, clear of the living; faces west, family faces east) | Teak jali vent in a frame: air passes freely (rooms with no sound-privacy need)
D12 | Kitchen to wet area | 2.5 | 7 | Hinged, single | Steel or WPC, lockable (the wet area is open to outside) | -
D17 | Kitchen entry (west, from the dining alcove; hinged at the north jamb) | 3 | 7 | Hinged, single | Teak frame, glazed upper panel, 3 ft (closes off cooking smoke) | -

## Windows
ID | Room | Wall faces | Width (ft) | Sill (ft) | Head (ft) | Height (ft) | Type | Status
W01 | Workstation | South | 5 | 3 | 7 |  | Timber jali + glazed shutters
W03 | Sitting and serving area | South | 5 | 3 | 7 |  | Timber jali + glazed shutters
W04 | Basin and crockery nook | South | 2.5 | 3.5 | 7 |  | Timber jali + glazed shutters (over the serving counter)
W17 | Pooja | East (to verandah) | 2.8 | 5.5 | 7 |  | High vent to the poomukham, jali + mesh (lamp smoke out)
W19 | Common bath | South | 2.2 | 5 | 7 |  | Frosted casement, top-hung vent
W05 | Kitchen | South | 3 | 3.5 | 7 |  | Timber jali + glazed shutters
W07 | Kitchen | South | 5 | 3.5 | 7 |  | Timber jali + glazed shutters
W08 | Kitchen | East | 2 | 3.5 | 7 |  | Timber jali + glazed shutters (2 ft, north end; hob wall kept solid)
W09 | Ensuite | North | 3 | 5 | 7 |  | Frosted casement
W10 | Ensuite | West | 4 | 5 | 7 |  | High jali vent
W11 | Master bedroom | North | 6 | 3 | 7 |  | Teak casement, glazed
W12 | Bedroom 2 | North | 6 | 3 | 7 |  | Teak casement, glazed (6 ft)
W13 | Bath 2 | North | 2.2 | 5 | 7 |  | Frosted casement, top-hung vent
W20 | Bedroom 2 |  | 4 | 7.5 | 9 |  | High jali vent to the sitting area, above the bed head (cross-ventilation with W12 and W03)
W18 | Dining bay | North | 6 | 3 | 7 |  | Teak casement, glazed (north light for the dining)
W14 | Living | North | 8 | 2 | 8 |  | Teak casement, tall, glazed
W16 | Basin and crockery nook | South | 2.5 | 3.5 | 7 |  | Timber jali + glazed shutters (over the serving counter)
SK1 | Roof | Up |  |  |  |  | Ventilator over dining, 5 x 5 ft, no glass: hipped tiled cap at 30 deg with 1'-6" overhang; 2 ft band of 45 deg louvres on all four sides; SS insect mesh behind; sealed inner shutters on a winding opener; 9 in upstand; lined shaft to the dining ceiling (see A-503)
GV1-3 | Roof | Up |  |  |  |  | Three glazed/jali vents in front gable (mukhappu), morning light into living

## Furniture
ID | Room | Item | Category | E-W (ft) | N-S (ft) | Qty | Material / spec | Est. unit cost (Rs) | Line total (Rs) | Chosen product / vendor | Status
F01 | Workstation | Work desk 5'6" x 2' (free-standing, cable tray) | Loose furniture | 1.9 | 5.5 | 1 | Teak or ply + veneer, cable tray
F02 | Workstation | Ergonomic task chair | Loose furniture | 1.2 | 1.2 | 1 | Mesh back
F03 | Workstation | Bookshelf, full height (video backdrop) | Built-in joinery | 1.2 | 7 | 1 | Teak / ply, open shelves
F04 | Master bay | Built-in wardrobe 6'-5", south wall, sliding doors, lofts above | Built-in joinery | 6.4 | 2 | 1 | Ply + laminate, 2 ft deep
F06 | Dressing alcove | Dresser with mirror (north wall) | Loose furniture | 3 | 0.8 | 1 | Teak
F45 | Dressing alcove | Built-in wardrobe, west wall, sliding doors | Built-in joinery | 2 | 5.2 | 1 | Ply + laminate, 2 ft deep
F07 | Ensuite | Vanity basin counter 3'-6" | Sanitary / plumbing | 3.5 | 1.5 | 1 | Granite top, wall-hung
F08 | Ensuite | WC (EWC) | Sanitary / plumbing | 1.8 | 1.2 | 1 | Wall-hung, concealed cistern
F09 | Ensuite | Shower glass partition | Sanitary / plumbing | 3.7 | 0.2 | 1 | 8 mm toughened glass
F10 | Master bedroom | Queen bed 5' x 6'6" + headboard | Loose furniture | 6.4 | 5 | 1 | Teak, head to east
F11 | Master bedroom | Bedside table | Loose furniture | 1 | 1 | 2 | Teak
F12 | Master bedroom | Reading chair | Loose furniture | 1.4 | 1.4 | 1 | Cane / upholstered
F54 | Master bedroom | Window seat / diwan 5' x 2' under the north window, drawers below | Loose furniture | 5 | 2 | 1 | Teak, cotton cushion
F16 | Common bath | WC (EWC), 17 in clear to the north wall | Sanitary / plumbing | 1.7 | 1.2 | 1 | Wall-hung on the wet wall shared with the wet area, concealed cistern
F17 | Common bath | Wash basin | Sanitary / plumbing | 0.7 | 1.2 | 1 | Wall-hung
F18 | Common bath | Shower glass partition (3 x 3 ft shower in the south-west corner) | Sanitary / plumbing | 0.15 | 2.6 | 1 | 8 mm toughened glass
F48 | Bath 2 | WC (EWC), 15 in clear each side of its centre | Sanitary / plumbing | 1.2 | 1.8 | 1 | Wall-hung on the north (outer) wall, concealed cistern
F49 | Bath 2 | Wash basin (south wall, dry zone) | Sanitary / plumbing | 1.5 | 0.7 | 1 | Wall-hung on the wet wall
F50 | Bath 2 | Fixed glass splash panel at the south edge of the 3' x 3'-6" wet zone (north-east) | Loose furniture | 1.5 | 0.15 | 1 | 8 mm toughened glass
F20 | Bedroom 2 | Queen bed 5' x 6'6" + headboard, head to the east wall (padded headboard: TV on the other side) | Loose furniture | 6.35 | 5 | 1 | Teak
F51 | Bedroom 2 | Bedside table | Loose furniture | 1 | 1 | 2 | Teak
F22 | Bedroom 2 | Work table 4' x 2' with monitor (east wall, north of the bed; north window to the side) | Loose furniture | 2 | 4 | 1 | Teak / ply, cable tray, monitor arm
F23 | Bedroom 2 | Built-in wardrobe 6' with a mirror door (west wall, shared with the master: also a sound buffer) | Built-in joinery | 2 | 6 | 1 | Ply + laminate
F24 | Dining | Dining table 5' x 3', 6-seat | Loose furniture | 5 | 3 | 1 | Teak or rosewood
F25 | Dining | Dining chair | Loose furniture | 1.1 | 1 | 6 | Teak + cane
F26 | Pooja | Pooja mandapam on the east wall (idols face west; family faces east) | Built-in joinery | 0.6 | 3 | 1 | Carved teak
F28 | Sitting and serving area | Built-in bench with storage drawers below | Loose furniture | 1.5 | 2.8 | 1 | Teak top, ply drawers, on legs
F29 | Wet area | Utility sink counter (on the kitchen wall) | Sanitary / plumbing | 1.7 | 2.5 | 1 | Kadappa / granite, SS sinks
F30 | Wet area | Washing machine bay 2' x 2' (covered back corner, 2 in clear of the bath wall) | Appliance / joinery | 1.9 | 1.9 | 1 | Splash-proof socket, floor drain
F31 | Wet area | Fold-away clothesline in the south walkway | Loose furniture | 4 | 1.8 | 1 | SS wire, wall brackets
F44 | Wet area | Tall slim utility cupboard (brooms, mops, detergents) | Built-in joinery | 1.2 | 1.2 | 1 | Ply + laminate on legs, louvred doors
F32 | Sitting and serving area | Hand-wash basin at the east end of the serving counter, just outside the common bath (after meals); mirror on the side wall | Sanitary / plumbing | 1.9 | 2 | 1 | Ceramic basin in granite top
F33 | Sitting and serving area | Serving counter with crockery cabinets above, 6 ft | Built-in joinery | 6 | 2 | 1 | Granite top, teak + glass shutters
F56 | Sitting and serving area | Tall storage cupboard 5' x 2' (bedding, suitcases, festival vessels), loft above | Built-in joinery | 5 | 2 | 1 | Ply + laminate, full height
F34 | Kitchen | L-counter, south run | Built-in joinery | 13.2 | 2 | 1 | Granite top, ply carcass
F35 | Kitchen | L-counter, east run (hob centred 7'-6" from the south wall face, on solid wall) | Built-in joinery | 2 | 7 | 1 | Granite top, cook faces east
F36 | Kitchen | Refrigerator space (kitchen north wall, behind the pooja, door facing south) | Appliance / joinery | 2.5 | 2.4 | 1 | Double-door, 2'6" wide
F55 | Kitchen | Tall pantry 4'-5" x 2' on the north wall (provisions, rice, vessels) | Loose furniture | 4.4 | 2 | 1 | Ply + laminate, full height with loft
F38 | Dining bay | Three-seat sofa 6'6" facing west to the TV | Loose furniture | 2.7 | 5.9 | 1 | Teak frame, cotton cushions
F39 | Dining bay | Coffee table 3'6" x 2' | Loose furniture | 2 | 3.5 | 1 | Teak
F53 | Dining bay | TV unit 4'-5" on Bedroom 2's east wall (55-65 in TV wall-mounted above) | Appliance / joinery | 1.3 | 4.4 | 1 | Teak, low, open shelves
F40 | Living | Armchair by the north window | Loose furniture | 2 | 1.6 | 1 | Cane / teak
F52 | Living | Shoe cupboard 3'-3" beside the main door (closed shutters, louvred for air) | Built-in joinery | 1.2 | 3.2 | 1 | Ply + laminate, 14 in deep
F41 | Poomukham (verandah) | Oonjal (swing) 3'6" | Loose furniture | 3.5 | 1.5 | 1 | Teak, chains to beam
F42 | Poomukham (verandah) | Arugu seat (built-in, south end) | Built-in joinery | 1.2 | 2.4 | 1 | Laterite base, teak top
Total
Note on I1: Your estimate per unit, in rupees. Leave blank until you have a quote.

## Finishes
Space | Floor | Walls | Ceiling | Notes | Decision
Living, dining, hall | Red oxide (IPS) or polished Kota / Tandur stone | 4 in flush skirting in floor stone; lime-finish or mineral paint | Sloped, follows roof, insulated board under deck | Stone hides dust better than glossy white tile
Bedrooms, offices, dressing | Matt vitrified 2x2 ft or red oxide | 4 in flush skirting; putty + washable emulsion | False ceiling at 9'-6", 50 mm insulation above | Ventilated attic above false ceiling
Pooja | White marble or teak | Teak panelling behind idol; 4 in marble skirting | Teak / board at 9'-6" | Idols on the east wall facing west (family faces east); lamp niche with heat-proof back
Kitchen | Anti-skid matt vitrified or Kota, mid-tone | Tile / stone full height between counter and wall cabinets | Moisture-resistant board at 9'-6" | Counter granite (local Ongole / Chimakurthy), 2 ft deep
Ensuite, Bath 2, common bath | Anti-skid ceramic (R11), falls 1:60 to drain | Tiles to 7 ft; full height in shower; waterproofing 12 in up all walls, 7 ft in shower | Moisture-resistant board / PVC at 8'-6" | 12 mm step down, no raised threshold; doors open outward; SS grab bars by the WC and in the shower
Wet area | Rough Cuddapah / Kota stone, falls to drain | 4 ft stone or tile dado | Open truss | 6 in kerb under jali wall stops rain blowing in
Family store, sitting area | Red oxide or vitrified | 4 in flush skirting; washable paint | Board at 9'-6"
Poomukham, steps | Flamed / leather-finish granite (not polished) | Granite skirting; plinth face clad 2 ft (splash zone) | Exposed rafters + board | Polished stone is slippery when wet
Exterior | Plinth apron: PCC 3 ft wide sloped away | AAC + 20 mm plaster with waterproof additive; elastomeric paint | - | Drip grooves under every sill and sunshade
Roof (all) | Mangalore clay tiles, every edge tile clipped / screwed | Membrane + 50 mm insulation on cement-fibre deck | Steel truss on RCC ring beam | Cyclone winds: tie trusses down with holding-down bolts

## Specification
Category | Element | Specification | Why (Guntur)
Substructure | Soil investigation | Min. 2 bore holes to 3 m or refusal; swell test, SBC | Black cotton soil swells when wet and shrinks when dry
Substructure | Foundations | As per engineer: footings below the active zone (often 1.5-2.5 m) or under-reamed piles; 300 mm sand/moorum cushion | Prevents seasonal heave cracking
Substructure | Plinth beam + DPC | RCC plinth beam all round; 40 mm DPC with waterproofing compound at plinth top | Stops rising damp into AAC
Substructure | Plinth fill | Non-expansive moorum / gravel in 150 mm layers, compacted; no black soil fill | Black soil under the floor will heave the slab
Substructure | Anti-termite | Pre-construction chemical treatment (IS 6313) at foundation, plinth fill and around walls | High termite risk; cannot be redone easily later
Substructure | Plinth protection | 3 ft PCC apron with slope away, joint sealed to wall | Keeps rain off expansive soil next to foundations
Frame | Columns, beams, bands | RCC frame; lintel band at door head, ring beam at wall top; seismic zone III detailing (IS 13920 as engineer decides) | AAC infill is not load-bearing for truss + cyclone loads
Walls | AAC blocks | IS 2185-3, 200 mm outer / 150 mm wet walls / 100 mm inner; thin-bed polymer mortar | Better insulation than brick; lighter frame
Walls | AAC to RCC joints | Galvanised mesh strip 150 mm wide over every block-concrete joint before plaster | The most common AAC crack; cheap to prevent
Walls | Chasing | Cut chases with a groover, never hammer; fill with polymer mortar + mesh | Hammering cracks AAC blocks
Walls | External plaster | 20 mm, two coats, waterproof admixture, cured 7 days; elastomeric paint | Wind-driven cyclone rain
Roof | Structure | Steel truss (hot-dip galvanised or epoxy primed), 30 deg pitch, bolted to ring beam with holding-down bolts | Uplift in cyclone winds
Roof | Deck and insulation | Cement-fibre board deck + 50 mm PIR/XPS or reflective insulation + membrane, then battens and Mangalore tiles | Cuts attic heat in 45 C summers
Roof | Tile fixing | Clip or screw every tile at eaves, verges, ridges and hips, and every 3rd row elsewhere; ridges bedded and pointed | Loose tiles fly in cyclones
Roof | Ventilation | Ridge / gable vents with bird and insect mesh; soffit vents at eaves | Flushes hot air from the attic
Roof | Dining ventilator | Steel frame bolted to the truss; hipped tiled cap at 30 deg, 1'-6" overhang; 45 deg timber or aluminium louvres with 4 in lap; SS 304 mesh about 1.2 mm (18 x 16) in a sealed continuous frame; inner shutters with EPDM seals and a winding opener at 5 ft; 9 in upstand with flashing; fibre-cement lined, insulated shaft | Lets hot air out, keeps out rain, mosquitoes and attic dust, and closes for AC
Roof | Gutters and downpipes | 150 mm half-round gutters with leaf guard, 100 mm downpipes at 8 points, to sump filter and recharge pit | Short heavy bursts; protects the plinth
Openings | Windows | Hardwood or UPVC frames; mosquito mesh on every opening; MS grill for security | Mosquitoes; ground-floor security
Openings | Sills and sunshades | External sills sloped 1:10 with drip groove; 2 ft sunshades with drip groove; 18 in projecting drip under the jali wall | Stops staining and water entry
Openings | Vents above inner doors | Pooja: open jali; bedrooms and bathrooms: none (the workstation has no door for now). 7'-6" to 9'-0" above the lintel band | Air moves with doors shut where privacy allows; bedrooms rely on their north windows, fans and AC
Openings | Bathroom doors | WPC / FRP shutters on WPC or granite frame base; no wooden frame touching the wet floor | Wood frames rot at the bottom
Floors | General | 4 in skirting flush with the wall plaster (groove in plaster); 3 mm epoxy grout in wet areas | No dust ledge, no black grout lines
Floors | Wet rooms | Waterproofing (polymer cementitious) floor + 12 in up walls + 7 ft in shower; flood test 48 h before tiling | Leak into neighbouring rooms is the top complaint
Plumbing | Supply | CPVC hot/cold; supply runs along external walls in clamps or shallow chases; isolation valve per bathroom and kitchen | Easy repair without breaking tiles
Plumbing | Drainage | uPVC SWR 110 mm soil, 75 mm waste; inspection chamber at every bend and junction; separate soil and grey-water lines | Easy rodding
Plumbing | Water treatment | RO for drinking at kitchen; whole-house softener if hardness > 300 mg/l; matt fittings | Guntur groundwater is often hard with high fluoride
Electrical | Wiring | FR-LSH copper; 1.5 sq mm lights, 2.5 sq mm sockets, 4 sq mm AC / geyser; separate circuits per AC | AC loads
Electrical | Protection | RCCB 30 mA + MCBs; 2 earth pits; surge protection device; DB in an accessible spot | Shock and lightning safety
Electrical | Backup | Inverter circuit to lights, fans, office sockets and router; conduit from roof to DB for future solar PV | Power cuts during work-from-home
Electrical | AC provisions | 16 A socket at 7 ft, 65 mm sleeve through wall, drain pipe to outside, ODU brackets on shaded walls | Retrofitting later means breaking walls

## Quantities
Group | Item | Qty | Unit | Basis | Rate (Rs / unit) | Amount (Rs)
Walls | AAC blocks, 200 mm outer walls | 22.94 | cu m | Net of openings, FFL to beam soffit
Walls | AAC blocks, 150 mm wet walls | 3.59 | cu m | Net of openings, FFL to beam soffit
Walls | AAC blocks, 100 mm inner walls | 6.18 | cu m | Net of openings, FFL to beam soffit
Frame | Plinth beam / lintel band / ring beam (each, running length) | 89.8 | m | Along all walls; sizes by engineer
Walls | Internal plaster | 286.5 | sq m | Both faces of inner walls, inner face of outer walls
Walls | External plaster (waterproof) | 146.6 | sq m | Outer walls + plinth face
Floors | Matt vitrified 2x2 | 47.1 | sq m | Clear room areas; add 5-8% wastage
Floors | Anti-skid ceramic, waterproofed | 10.9 | sq m | Clear room areas; add 5-8% wastage
Floors | Red oxide / Kota stone | 38.7 | sq m | Clear room areas; add 5-8% wastage
Floors | Rough Cuddapah / Kota, falls | 2.4 | sq m | Clear room areas; add 5-8% wastage
Floors | Anti-skid matt vitrified | 11.5 | sq m | Clear room areas; add 5-8% wastage
Floors | Marble / teak (pooja) | 1.1 | sq m | Clear room areas; add 5-8% wastage
Floors | Flamed granite | 6.1 | sq m | Clear room areas; add 5-8% wastage
Floors | Flush skirting, 4 in | 111.7 | m | Room perimeters (dry rooms), doors not deducted
Wet rooms | Wall tiles to 7 ft, Ensuite | 15.6 | sq m | Full height in the shower adds ~2 sq m
Wet rooms | Waterproofing, Ensuite | 9.8 | sq m | Floor + 12 in upturn + shower walls to 7 ft
Wet rooms | Wall tiles to 7 ft, Common bath | 13.2 | sq m | Full height in the shower adds ~2 sq m
Wet rooms | Waterproofing, Common bath | 8.5 | sq m | Floor + 12 in upturn + shower walls to 7 ft
Wet rooms | Wall tiles to 7 ft, Bath 2 (attached to Bedroom 2) | 15.1 | sq m | Full height in the shower adds ~2 sq m
Wet rooms | Waterproofing, Bath 2 (attached to Bedroom 2) | 9.6 | sq m | Floor + 12 in upturn + shower walls to 7 ft
Kitchen | Granite counter, 2 ft deep | 5.4 | m | South and east runs (F34, F35)
Kitchen | Dado between counter and wall cabinets | 3.3 | sq m | 2 ft high
Roof | Sloped roof area (tiles, deck, insulation, membrane) | 194.1 | sq m | Hip outline / cos 30 deg; add ~8% for gable and laps
Roof | Gutters | 40.8 | m | Both long eaves
Roof | Downpipes, 100 mm | 8 | no. | About 12 ft each
Roof | Ridge and hip tiles | 35.5 | m | Approximate
Site | Plinth protection apron, 3 ft wide | 51 | sq m | PCC with slope away
Openings | Doors | 9 | no. | See Doors tab
Openings | Windows and vents | 17 | no. | See Windows tab
Openings | Window area (for mesh and grills) | 22.8 | sq m
Total of priced items
Note on F1: Fill from local contractor or supplier quotes. Quantities are approximate take-offs from the model.

## Electrical
Code | Item | Mounting height | Room | X (ft) | Y (ft) | Note
F | Ceiling fan point | ceiling | Workstation (open, walls optional later) | 9.5 | 7
L | Ceiling light | ceiling | Workstation (open, walls optional later) | 9.5 | 9.5
L | Ceiling light | ceiling | Workstation (open, walls optional later) | 9.5 | 4.5
S | Switchboard | 4'-0" | Workstation (open, walls optional later) | 5.4 | 10.4
U | Inverter (UPS) socket | 1'-0" | Workstation (open, walls optional later) | 13 | 5 | floor box under the desk
D | Data point (Cat6) | 1'-0" | Workstation (open, walls optional later) | 13 | 6 | floor box under the desk
P | 6 A socket | 1'-0" | Workstation (open, walls optional later) | 13 | 8 | floor box under the desk
AC | AC indoor unit (16 A socket, sleeve, drain) | 7'-6" | Workstation (open, walls optional later) | 5.6 | 7 | west wall, above the bookshelf
ODU | AC outdoor unit bracket | 7'-0" outside | Workstation (open, walls optional later) | 4.2 | 6.5 | west wall, high
L | Ceiling light | ceiling | Master bay (old store, open to the bedroom) | 17.5 | 7.5
P | 6 A socket | 1'-0" | Master bay (old store, open to the bedroom) | 14.5 | 8.6
P | 6 A socket | 1'-0" | Master bay (old store, open to the bedroom) | 20.6 | 8.6
L | Ceiling light | ceiling | Dressing alcove | 8.25 | 14
WL | Wall light / mirror light | 6'-6" | Dressing alcove | 5.4 | 14 | mirror
P | 6 A socket | 1'-0" | Dressing alcove | 5.4 | 16.4 | hair dryer
L | Ceiling light | ceiling | Ensuite | 8.25 | 20.5
EF | Exhaust fan | 7'-0" | Ensuite | 5.4 | 24 | out through west wall
G | Geyser (16 A) | 6'-6" | Ensuite | 8.3 | 24.6 | over shower
PC | 6 A socket at counter | 3'-6" | Ensuite | 10.9 | 18.6 | shaver, by basin
S | Switchboard | 4'-0" | Master bedroom | 11.9 | 22 | ensuite switches outside the door
F | Ceiling fan point | ceiling | Master bedroom | 17.4 | 14.7 | over the bed
L | Ceiling light | ceiling | Master bedroom | 18 | 23.5
L | Ceiling light | ceiling | Master bedroom | 13 | 13.5
L | Ceiling light | ceiling | Master bedroom | 13 | 23.5
S | Switchboard | 4'-0" | Master bay (old store, open to the bedroom) | 20.6 | 9.4 | at the suite door, 2-way
S | Switchboard | 4'-0" | Master bedroom | 20.6 | 18 | bedside, 2-way
P | 6 A socket | 1'-0" | Master bedroom | 20.6 | 11.6 | bedside
P | 6 A socket | 1'-0" | Master bedroom | 20.6 | 17.6 | bedside
AC | AC indoor unit (16 A socket, sleeve, drain) | 7'-6" | Master bedroom | 11.9 | 18 | west wall, throws along the bed, not on the head
ODU | AC outdoor unit bracket | 7'-0" outside | Master bedroom | 16 | 25.6 | north wall, shaded
L | Ceiling light | ceiling | Bath 2 (attached to Bedroom 2) | 24.5 | 21.2
EF | Exhaust fan | 7'-0" | Bath 2 (attached to Bedroom 2) | 25.6 | 24.6 | out through the north wall
G | Geyser (16 A) | 6'-6" | Bath 2 (attached to Bedroom 2) | 27.6 | 23.6 | over shower, east wall
PC | 6 A socket at counter | 3'-6" | Bath 2 (attached to Bedroom 2) | 23.4 | 18.4 | by basin
S | Switchboard | 4'-0" | Bedroom 2 | 28.4 | 21.3 | Bath 2 switches outside the bath door
P | 6 A socket | 1'-0" | Master bedroom | 12.2 | 24.6 | reading chair
L | Ceiling light | ceiling | Pooja | 59 | 15
WL | Wall light / mirror light | 6'-6" | Pooja | 60.4 | 15 | lamp niche above the idols
P | 6 A socket | 1'-0" | Pooja | 57.4 | 16.6
S | Switchboard | 4'-0" | Living | 56.6 | 16.9 | pooja switches outside, living side
L | Ceiling light | ceiling | Sitting and serving area (open) | 39 | 6.5
PC | 6 A socket at counter | 3'-6" | Sitting and serving area (open) | 35.15 | 3.4 | serving counter
PC | 6 A socket at counter | 3'-6" | Sitting and serving area (open) | 38.1 | 3.4 | serving counter
L | Ceiling light | ceiling | Common bath | 44.7 | 6.2
EF | Exhaust fan | 7'-0" | Common bath | 46.9 | 3.4 | out through the south wall
G | Geyser (16 A) | 6'-6" | Common bath | 41.8 | 4.5 | over shower, west wall (clear of the window)
PC | 6 A socket at counter | 3'-6" | Common bath | 47.6 | 6 | by basin
S | Switchboard | 4'-0" | Sitting and serving area (open) | 41.1 | 9.2 | common bath switches outside the door
F | Ceiling fan point | ceiling | Bedroom 2 | 34.6 | 16.5 | over the bed
WL | Wall light / mirror light | 6'-6" | Bedroom 2 | 37.6 | 16.5 | reading light over the bed head
L | Ceiling light | ceiling | Bedroom 2 | 24 | 14
L | Ceiling light | ceiling | Bedroom 2 | 34 | 14
L | Ceiling light | ceiling | Bedroom 2 | 33 | 20.5
S | Switchboard | 4'-0" | Bedroom 2 | 36.8 | 11.4 | at the door (latch side, on the corner return), 2-way
S | Switchboard | 4'-0" | Bedroom 2 | 37.6 | 13 | bedside, 2-way
P | 6 A socket | 1'-0" | Bedroom 2 | 37.6 | 13.5 | bedside
P | 6 A socket | 1'-0" | Bedroom 2 | 37.6 | 19.5 | bedside
S | Switchboard | 4'-0" | Bedroom 2 | 37.6 | 19.9 | bedside, 2-way
P | 6 A socket | 1'-0" | Bedroom 2 | 37.6 | 20.8 | work table
U | Inverter (UPS) socket | 1'-0" | Bedroom 2 | 37.6 | 21.6 | work table, monitor
D | Data point (Cat6) | 1'-0" | Bedroom 2 | 37.6 | 22.4 | work table
U | Inverter (UPS) socket | 1'-0" | Bedroom 2 | 37.6 | 23.2 | work table
AC | AC indoor unit (16 A socket, sleeve, drain) | 7'-6" | Bedroom 2 | 28.4 | 24 | high on the bath's east wall near the north corner, throws east toward the bed foot
WL | Wall light / mirror light | 6'-6" | Sitting and serving area (open) | 41.1 | 4.4 | over basin, on the common bath wall
ODU | AC outdoor unit bracket | 7'-0" outside | Bedroom 2 | 29.5 | 25.6 | north wall, shaded
L | Ceiling light | ceiling | Dining bay (north window) | 41.5 | 21.5
F | Ceiling fan point | ceiling | Dining bay (north window) | 45 | 21.5 | long downrod, over the seating
P | 6 A socket | 1'-0" | Dining bay (north window) | 48.6 | 24.6
TV | TV + data point | 3'-6" | Dining bay (north window) | 38.4 | 22.4 | TV wall: 2 sockets + data + HDMI conduit to the unit
P | 6 A socket | 1'-0" | Dining bay (north window) | 38.4 | 21 | TV unit
AC | AC indoor unit (16 A socket, sleeve, drain) | 7'-6" | Dining bay (north window) | 38.4 | 20 | above the TV unit, throws east over the seating
ODU | AC outdoor unit bracket | 7'-0" outside | Dining bay (north window) | 40 | 25.6 | north wall, shaded
L | Ceiling light | ceiling | Dining | 44.5 | 15 | pendant
WL | Wall light / mirror light | 6'-6" | Dining | 38.4 | 17.5
P | 6 A socket | 1'-0" | Dining | 38.4 | 16.2
S | Switchboard | 4'-0" | Dining | 38.4 | 13.7 | dining and bay, at the passage
L | Ceiling light | ceiling | Sitting and serving area (open) | 30.5 | 6.75
S | Switchboard | 4'-0" | Sitting and serving area (open) | 21.4 | 6
INV | Inverter + battery | floor | Sitting and serving area (open) | 22 | 5 | lithium inverter in a ventilated cabinet under the bench
L | Ceiling light | ceiling | Wet area (open to the walkway) | 50 | 5.5 | weatherproof
P16 | 16 A power socket | varies | Wet area (open to the walkway) | 48.5 | 8.7 | washing machine
P | 6 A socket | 1'-0" | Wet area (open to the walkway) | 52.6 | 6 | utility, weatherproof
L | Ceiling light | ceiling | Kitchen | 62 | 8
WL | Wall light / mirror light | 6'-6" | Kitchen | 61 | 3.5 | under-cabinet
WL | Wall light / mirror light | 6'-6" | Kitchen | 66.5 | 9.6 | under-cabinet
CH | Kitchen chimney point (16 A) | 7'-0" | Kitchen | 66.6 | 7.5 | 3 ft chimney on solid wall, duct out through the east wall
P16 | 16 A power socket | varies | Kitchen | 58.75 | 12.7 | refrigerator, behind the fridge
PC | 6 A socket at counter | 3'-6" | Kitchen | 54.5 | 3.5
PC | 6 A socket at counter | 3'-6" | Kitchen | 58 | 3.5 | microwave / OTG
PC | 6 A socket at counter | 3'-6" | Kitchen | 63.5 | 3.5 | mixer
PC | 6 A socket at counter | 3'-6" | Kitchen | 66.6 | 5.6
PC | 6 A socket at counter | 3'-6" | Kitchen | 66.6 | 9.6
PC | 6 A socket at counter | 3'-6" | Kitchen | 59.3 | 3.5 | RO purifier, by sink
S | Switchboard | 4'-0" | Kitchen | 53.4 | 9 | beside the entry, latch side
F | Ceiling fan point | ceiling | Living | 55 | 19 | long downrod
L | Ceiling light | ceiling | Living | 52 | 22.5
L | Ceiling light | ceiling | Living | 55 | 16
P | 6 A socket | 1'-0" | Dining bay (north window) | 48.2 | 18.4 | floor socket, sofa end
P | 6 A socket | 1'-0" | Living | 52.6 | 17.8 | floor socket, armchair
S | Switchboard | 4'-0" | Living | 60.6 | 21 | main switch at door
DB | Distribution board | 5'-0" to top | Dining | 38.4 | 12.6 | dining face of Bedroom 2's east wall, by the passage; dry wall away from the pooja and wet area
U | Inverter (UPS) socket | 1'-0" | Dining | 38.4 | 14.6 | router (central)
L | Ceiling light | ceiling | Poomukham (verandah) | 64 | 16
L | Ceiling light | ceiling | Poomukham (verandah) | 64 | 22
BELL | Bell push | 4'-6" | Poomukham (verandah) | 61.4 | 20.4
CAM | CCTV point | 8'-0" | Poomukham (verandah) | 66.5 | 24.6 | covers gate and door
P | 6 A socket | 1'-0" | Poomukham (verandah) | 61.4 | 24 | outdoor, weatherproof
S | Switchboard | 4'-0" | Poomukham (verandah) | 61.4 | 20.9
MTR | Meter at gate | 5'-0" | Site | 74.6 | 23 | meter in compound wall by gate
GL | Outdoor / gate light | 7'-0" | Site | 74.6 | 14.5 | gate light
EP | Earth pit | ground | Site | 68.2 | 1.5 | earth pit 1
EP | Earth pit | ground | Site | 73.5 | 1.5 | earth pit 2
GL | Outdoor / gate light | 7'-0" | Site | 2.5 | 8 | rear garden

## Plumbing
Code | Item | Room | X (ft) | Y (ft) | Note
WC | Wall-hung WC, concealed cistern | Ensuite | 6.3 | 19.5 | wall-hung on west (outer) wall
HF | Health faucet | Ensuite | 5.4 | 20.6
BS | Wash basin | Ensuite | 9 | 17.8 | on 7 in wet wall
SH | Shower mixer (hot + cold) | Ensuite | 5.4 | 23.6
FT | Floor trap / linear drain | Ensuite | 8.25 | 24.5 | linear drain along north wall
FT | Floor trap / linear drain | Ensuite | 9.6 | 20.2 | dry zone trap
WC | Wall-hung WC, concealed cistern | Common bath | 47.6 | 7.35 | on the wet wall
HF | Health faucet | Common bath | 47.6 | 6.5
BS | Wash basin | Common bath | 47.6 | 4.8 | on 7 in wet wall
SH | Shower mixer (hot + cold) | Common bath | 41.8 | 3.9 | west wall, clear of the window
FT | Floor trap / linear drain | Common bath | 43.2 | 3.6 | shower drain
FT | Floor trap / linear drain | Common bath | 46.3 | 6 | dry zone trap
WC | Wall-hung WC, concealed cistern | Bath 2 (attached to Bedroom 2) | 22.5 | 24 | on the north (outer) wall, 15 in clear each side
HF | Health faucet | Bath 2 (attached to Bedroom 2) | 21.4 | 23.4
BS | Wash basin | Bath 2 (attached to Bedroom 2) | 22.35 | 18.4 | on 7 in wet wall (south)
SH | Shower mixer (hot + cold) | Bath 2 (attached to Bedroom 2) | 27.6 | 24 | east wall
FT | Floor trap / linear drain | Bath 2 (attached to Bedroom 2) | 26.3 | 24.3 | linear drain along the north wall
FT | Floor trap / linear drain | Bath 2 (attached to Bedroom 2) | 24.6 | 19.7 | dry zone trap
SK | Sink | Wet area (open to the walkway) | 51.85 | 4.6 | utility sink
WM | Washing-machine inlet + drain | Wet area (open to the walkway) | 49.35 | 7.85
FT | Floor trap / linear drain | Wet area (open to the walkway) | 49.8 | 3.6 | floor falls out to the walkway
TAP | Tap | Wet area (open to the walkway) | 52.6 | 3.4 | bucket tap, low
BS | Wash basin | Sitting and serving area (open) | 40.2 | 4.3 | hand-wash basin outside the common bath, waste straight out to the south walkway
SK | Sink | Kitchen | 60.5 | 3.5 | single bowl + drainboard, under window
RO | RO purifier point | Kitchen | 59.3 | 3.5
FT | Floor trap / linear drain | Kitchen | 64 | 12.5 | cleaning trap
TAP | Tap | Site | 69.6 | 13.6 | foot-wash tap at steps
TAP | Tap | Site | 4.4 | 10 | garden tap
TAP | Tap | Site | 71.2 | 22 | tulsi / garden tap
IC | Inspection chamber | Site | 3.6 | 19.5 | IC-1 soil
IC | Inspection chamber | Site | 46.8 | 1.8 | IC-2 soil
IC | Inspection chamber | Site | 3.6 | 26.6 | IC-3 soil
IC | Inspection chamber | Site | 12 | 26.6 | IC-4 soil
GT | Grease trap | Site | 60.5 | 1 | grease trap
IC | Inspection chamber | Site | 49.8 | 1 | IC-5 grey
IC | Inspection chamber | Site | 3.6 | 1.8 | IC-6 soil bend
IC | Inspection chamber | Site | 4.2 | 1 | IC-7 grey
IC | Inspection chamber | Site | 4.2 | 26 | IC-8 grey
IC | Inspection chamber | Site | 9.6 | 26 | IC-9 ensuite grey
IC | Inspection chamber | Site | 22.5 | 26.6 | IC-10 Bath 2 soil
IC | Inspection chamber | Site | 26.4 | 26 | IC-11 Bath 2 grey

## Checklist
Area | Common mistake | Do instead | Shown on | Status
Whole house: structure and site (Guntur) | Ordinary shallow footings on black cotton soil: walls crack after the first monsoon as the soil swells and shrinks. | Get a soil test first. Take footings below the active zone or use under-reamed piles, tie them with a plinth beam, and put a sand cushion under it. | A-301, A-501/1
Whole house: structure and site (Guntur) | Filling the plinth with the black soil dug out of the foundations: the floor heaves and cracks. | Fill with moorum or gravel compacted in 150 mm layers. Cart the black soil away or use it in the garden. | A-501/1
Whole house: structure and site (Guntur) | Rainwater, garden beds and soak pits right next to the walls. | Lay a 3 ft paved apron sloping away, run gutters to the sump, and keep soak pits and septic 6 ft+ away (here they are in the north strip). | A-101, P-101
Whole house: structure and site (Guntur) | Planting neem, mango or coconut trees close to the house for shade: roots dry the soil and the walls crack. | Keep big trees 8 ft+ away (ideally their mature height). Shade the west wall with a creeper pergola instead. | A-101
Whole house: structure and site (Guntur) | Plinth set at road level on farm land: roads and neighbouring plots get raised later and rain flows in. | FFL 2 ft above finished ground and at least 18 in above the road crown. Survey levels before fixing it. | A-001, A-301
Whole house: structure and site (Guntur) | Skipping the anti-termite treatment or doing it after the floor. | Treat before the plinth fill, at each fill layer and along the walls; get a certificate with a warranty. | A-001
Whole house: structure and site (Guntur) | Treating AAC like brick: no mesh at joints, chases cut with a hammer. Hairline cracks appear everywhere. | Put a mesh strip over every block-to-concrete joint, cut chases with a machine, and use thin-bed mortar. | A-502/8
Whole house: structure and site (Guntur) | No lintel band or ring beam: risky in seismic zone III, and the roof trusses have nothing solid to bolt to. | Run a continuous RCC lintel band at door height and a ring beam at wall top with holding-down bolts. | A-301, A-501/4
Whole house: structure and site (Guntur) | No record of where pipes and wires run: someone drills into a pipe years later. | Photograph every wall with a tape measure in view before plaster and keep the photos with the drawings. | A-001
Poomukham and entrance | Polished granite on steps and verandah: slippery when wet. | Use flamed or leather-finish granite and give steps a nosing. | A-105
Poomukham and entrance | Uneven steps (the last one different), which make people trip. | Make all risers 6 in and treads 12 in, with 3 equal risers from ground to verandah. | A-202, A-301
Poomukham and entrance | Verandah floor at the same level as the house: wind-driven rain runs in under the main door. | Set the poomukham 6 in lower, sloping out 1:100, with a raised weather bar under the main door. | A-105, A-502/9
Poomukham and entrance | No place to wash feet or leave footwear: mud and dust come inside. | Put a foot-wash tap with a small drain beside the steps, and keep a shoe cupboard just inside the main door (here between the door and the pooja wall). | P-101, A-103
Poomukham and entrance | Oonjal (swing) hung later from the roof purlins. | Cast or bolt swing hooks into the verandah beam, rated for 200 kg, before the roof goes on. | A-103
Poomukham and entrance | Bell, CCTV and outdoor light added later with surface wiring. | Run conduits now to the bell, camera, gate light and intercom. | E-101, E-102
Living | TV on a wall facing a window, so glare washes it out. | Put the TV on the east wall of the living, with the big north window to the side and no window behind or opposite the screen; run a conduit to the router. | A-103, E-102
Living | Too few sockets, leading to extension cords across the floor. | Fit sockets at both sofa ends, 2 at the TV, and a router socket on the inverter circuit. | E-102
Living | Fan on a short rod under a high sloped ceiling: weak breeze. | Use a long downrod so the blades sit about 9 ft above the floor, hung from a hook fixed to the truss. | E-101
Living | Large west or south glazing: the room overheats in April-May. | Glaze to the north; light from the east comes in through the main door and poomukham; south only through jalis and sunshaded windows. | A-201
Living | Main door swinging into the sofa or the DB. | Check door swings against the furniture; put the DB away from the door and the pooja (here on the dining face of Bedroom 2's east wall). | A-103, E-102
Dining and ventilator | Glass skylight over the dining: a greenhouse in Guntur summers that leaks and needs constant cleaning. | No glass. Light comes in from the living, the nook's south window and the hall; a raised ventilator with a solid insulated roof and louvres on all four sides lets the hot air rising from the house escape. | A-106, A-301
Dining and ventilator | Flat-topped roof ventilator: water ponds, leaves and droppings collect, and it leaks first. | Give it a small hipped roof at the main roof pitch, tiled and clipped, with a 1'-6" overhang and drip edge. | A-503
Dining and ventilator | Flat or shallow louvres: cyclone rain blows straight through. | 45 deg blades sloping down and out with a 4 in lap (no straight line through), on a sill sloped out 1:10 with a drip. | A-503
Dining and ventilator | Relying on louvres to stop mosquitoes: they don't. | SS 304 mesh about 1.2 mm (18 x 16) in a continuous frame sealed at every corner, reachable from inside for cleaning. | A-503
Dining and ventilator | Vent shutters that leak, or need a ladder to open. | Inner shutters with rubber (EPDM) seals so AC air stays in, worked by a winding handle or cord at hand height. | A-503
Dining and ventilator | Ventilator opening straight into the roof space: attic heat and dust pour into the dining. | Line the shaft from the dining ceiling to the ventilator sill with insulated fibre-cement board. | A-503, A-301
Dining and ventilator | Dining and hall feel dim with no skylight. | Use light wall and ceiling colours; the dining is now open to the living, the 6 ft hall and the nook window. If it still feels dark after move-in, a sun tube can be added later with little work. | E-101
Dining and ventilator | Table too big for the room: chairs hit the walls. | Clear size is about 8'9" x 7'6". A 6-seat 5 x 3 ft table leaves about 2'3" each side, so use a 4-seat or round table, or let it spill into the hall. | A-104
Hand-wash basin (serving counter) | Painted wall behind the basin: stains and peeling. | Put a stone or tile splash-back 2 ft high above the basin. | A-502/7
Hand-wash basin (serving counter) | Basin too high or low, or on a pedestal that traps dirt. | Use a wall-hung basin with the rim at 32 in and a bottle trap, so the floor stays clear. | A-502/7
Hand-wash basin (serving counter) | Light behind the mirror, which leaves faces in shadow; socket next to the tap. | Put the light above the mirror and keep the socket 2 ft from the tap at 42 in. | A-502/7, E-101
Kitchen | Counter at the Western 36 in height: tiring for Indian cooking with tall vessels. | Make the counter 34 in, with a 30-31 in section for grinding and rolling chapatis. | A-502/6
Kitchen | White glossy floor and counter: shows every turmeric stain and is slippery with oil. | Use a mid-tone matt floor and a granite counter (local Chimakurthy / Ongole). | A-105
Kitchen | Chimney duct with long bends: weak suction and grease build-up. | Hob on the east run with the chimney ducted straight out through the east wall. | A-502/6, E-102
Kitchen | Too few counter sockets. | Fit 5-6 sockets at 42 in plus 16 A for the fridge, microwave / OTG and chimney; RO point by the sink. | E-102
Kitchen | Base cabinets standing on the floor: rot and termites. | Put cabinets on 4 in legs or a granite plinth. | A-502/6
Kitchen | Gas cylinder in a closed cabinet under the hob. | Keep the cylinder in the ventilated wet area with a fixed copper / steel line and a valve through the wall. | A-103
Kitchen | Kitchen drain without a grease trap: chokes within a year. | Put a grease trap outside, before any junction. | P-101
Kitchen | Fridge beside the hob or in direct sun. | Fridge on the kitchen's north wall behind the pooja, beside the tall pantry and well away from the hob; nothing blocks the counter. | A-103
Wet area, storage and kitchen entry | A narrow kitchen entry squeezed past a TV wall: two people can't pass and serving is awkward. | The kitchen is entered through a 3 ft hinged door on its west side, straight off the dining alcove: one short trip for serving, and it closes off cooking smoke. The pooja front stays quiet. | A-102
Wet area, storage and kitchen entry | Open wet area floods during heavy rain, or becomes a back door for intruders. | Keep its floor 3 in below the house, sloping out to the walkway drain; washing machine in the covered back corner; a lockable steel or WPC door into the kitchen, and a back gate in the compound wall. | A-105, A-502/9
Wet area, storage and kitchen entry | Washing machine with no tap, drain or socket at the right height. | Provide a tap at 3 ft, a floor drain behind the machine and a splash-proof 16 A socket at 4 ft. | P-101, E-102
Wet area, storage and kitchen entry | No separate store means provisions end up on the floor. | Use the storage-bench drawers in the sitting area, lofts above the master bay and kitchen, tall kitchen cabinets; keep rice and grain in sealed bins off the floor. | A-103
Wet area, storage and kitchen entry | Inverter batteries in a bedroom or a closed cupboard. | Use a lithium inverter battery in a ventilated cabinet under the sitting-area bench, away from water and bedrooms. | E-102
Pooja | Lamp smoke blackens the ceiling and the teak panelling. | Fit a heat-proof granite or brass back panel behind the diya and a small high vent; use a washable ceiling finish. | A-105
Pooja | Pooja sharing a wall with a toilet. | Here the pooja sits in the living's south-east corner, back to back with the kitchen (no toilet on any side). It opens west into the living with doors that open inward, idols on its east wall, so the family faces east; the floor is 3 in higher. | A-102
Pooja | Polished marble floor that becomes slippery with oil. | Use honed (matt) marble or teak. | A-105
Bedrooms | AC indoor unit above the bed head: cold air blows on your head all night. | Mount the AC on a side or opposite wall, throwing across the bed. | E-102
Bedrooms | Only one switchboard at the door. | Add 2-way switches at the bed for the light and fan, plus bedside sockets. | E-101, E-102
Bedrooms | Wardrobe shallower than 2 ft: hangers do not fit. | Make wardrobes 2 ft deep with lofts above to the false ceiling. | A-103
Bedrooms | 2'-6" bedroom doors: a mattress or cupboard cannot go in later. | Make bedroom doors 3'-0". | A-401
Bedrooms | Curtain rods, TV brackets and fan hooks screwed into plain AAC, which pulls out. | Fix timber grounds or use AAC-rated anchors, marked before plaster. | A-001
Bedrooms | Windows without mesh, so mosquito coils every night. | Put insect mesh on a separate frame on every opening. | A-401
Wardrobes and dressing | Dark, unventilated store: provisions smell musty in the monsoon and attract insects. | High jali vent with mesh, a jali above the door, shelves on legs, a light and a socket. | A-401, E-102
Wardrobes and dressing | Clothes stored in a separate walk-in only one person can use, while the house has no store. | Here the old walk-in is an open wardrobe bay of the master bedroom (sliding wardrobe with lofts), plus a wardrobe in the dressing alcove. | A-103
Wardrobes and dressing | Dressing mirror lit from behind. | Mount the mirror light above or beside the mirror. | E-101
Bathrooms | Raised step at the bathroom door, which people trip on at night. | Drop the bathroom 12 mm with a sloped granite threshold and no step. | A-502/5
Bathrooms | Whole floor sloped to one trap: the entire bathroom is always wet. | Separate wet and dry zones: a linear drain in the shower, the dry zone nearly flat, and a glass partition. | A-502/5
Bathrooms | No waterproofing or flood test: damp skirting in the next bedroom within a year. | Waterproof the floor, 12 in up the walls and 7 ft in the shower, then do a 48 h flood test before tiling. | A-502/5, A-001
Bathrooms | Wooden door frame standing in the wet floor. | Use a WPC / FRP shutter with the frame on a granite or WPC block. | A-401, A-502/9
Bathrooms | Exhaust fan blowing into the false ceiling. | Duct the exhaust fan straight out through the outer wall. | E-101
Bathrooms | Geyser hidden above the false ceiling, which can't be serviced. | Wall-mount it at 6'-6" with the switch outside; leave a ceiling access panel at the concealed cistern. | E-102
Bathrooms | Black or glossy tiles and chrome fittings with Guntur's hard water: white scale shows everywhere. | Use light matt tiles and matt / PVD fittings, plus a softener if hardness is high. | A-105, P-101
Bathrooms | Ensuite squeezed to 5 ft wide: about 4'-5" clear, too tight for standard fittings. | Widened by 1'-6" into the master (about 6'-0" clear): WC on the outer wall, 3'-6" vanity on the wet wall, walk-in shower across the north end. The door opens clear of all three. | A-103, A-104
Bathrooms | No backing for grab bars later. | Fix blocking in the walls beside the WC and shower now. | A-502/5
Work spaces (master-suite workstation and Bedroom 2 table) | Window behind the screen (silhouette on video calls) or in front of it (glare). | Put the desk side-on to the window: the workstation gets south light from the side; in Bedroom 2 the table faces the bath wall with the north window to the side. | A-103
Work spaces (master-suite workstation and Bedroom 2 table) | Not enough power or data. | Fit 2 UPS sockets, 1 normal socket and a Cat6 point at each desk (workstation and Bedroom 2 table), with the router on the inverter. | E-102
Work spaces (master-suite workstation and Bedroom 2 table) | An open workstation in the master suite: calls disturb whoever is resting. | Walls are left out for now and drawn dashed; if calls become a problem, add the two walls and a sliding glass door later (conduit and lintel can be provided now). | A-401
Work spaces (master-suite workstation and Bedroom 2 table) | Bare wall behind you on video calls. | Put a bookshelf behind the chair as the backdrop. | A-103
Doors and windows | Solid walls and closed doors between the north and south rooms: no breeze crosses the house at night or during calls. | Put a vent above inner doors, 7'-6" to 9'-0": open jali for the pooja; none on the lockable door to the open wet area. | A-401
Doors and windows | Open vents above bedroom and bathroom doors: conversation, TV and smells carry into the hall and the next room. | No vents at bedrooms (their big north windows, ceiling fans and AC are enough for rooms this shallow) or bathrooms (the door's bottom louvre feeds the exhaust fan); the office gets a sealed glazed flap. | A-401
Doors and windows | A 3'-6" hall: two people can't pass, and furniture won't turn the corner. | Here both bedrooms open off the 15 ft sitting area instead of a narrow hall, so no corridor space is wasted. | A-104
Doors and windows | No drip groove under sills and sunshades: black streaks down the walls. | Slope every external sill 1:10 with a drip groove, and give every chajja a drip groove under its edge. | A-501/3
Doors and windows | Unseasoned teak that warps and jams. | Use kiln-seasoned wood, or sal / pinkado frames and UPVC on the wet side. | A-401
Doors and windows | Mild-steel hinges and screws that rust with humidity and hard water. | Use SS 304 hardware, with magnetic stoppers on every door. | A-401
Doors and windows | Grill with no openable section: no way out in a fire. | Give each bedroom one escape window with an openable grill. | A-401
Floors, walls and finishes | Skirting stuck on top of the plaster: a dust ledge that also chips. | Set the skirting flush with the plaster face, with a groove above it. | A-501/2
Floors, walls and finishes | Tiles laid tight to the walls: they pop up (tenting) in 45 C summers. | Leave 5 mm gaps at walls and movement joints every 15-20 ft, hidden by the skirting. | A-501/2, A-105
Floors, walls and finishes | Cement grout in bathrooms turns black. | Use epoxy grout in wet areas. | A-001
Floors, walls and finishes | Exterior paint that chalks and fades in strong sun. | Use a waterproof plaster additive and elastomeric or UV-stable exterior paint. | A-601
Roof and rainwater | Clay tiles just resting on battens: a cyclone strips the edges first. | Clip or screw every eave, verge, hip and ridge tile, plus every third row elsewhere. | A-106, A-501/4
Roof and rainwater | Water creeping back under the eave tiles and into the soffit. | Use a fascia with drip-edge flashing turned down into the gutter, and raise the first tile row on a tilting fillet. | A-501/4
Roof and rainwater | No gutters: roof water splashes the plinth and soaks the foundation. | Gutters on both long eaves, downpipes into the sump filter and recharge pit. | A-106, P-101
Roof and rainwater | Valleys and skylight edges sealed only with mortar or sealant. | Use 600 mm metal valley gutters, and a 9 in upstand with flashing at the ventilator. | A-106
Roof and rainwater | No insulation under Mangalore tiles: rooms radiate heat until midnight. | Add 50 mm insulation on the deck, ventilate the attic at ridge and soffits, and fit insulated false ceilings in bedrooms. | A-301, A-501/4
Roof and rainwater | Birds, bats and rats nesting in the roof. | Bird stops at the eaves and mesh at ridge vents and soffits. | A-501/4
Electrical | One circuit for everything; cheap wire. | Separate MCBs for each AC, geyser, kitchen and pump; RCCB 30 mA; FR-LSH copper wire sized per load. | E-102
Electrical | No inverter wiring planned, so it gets rewired later. | Put lights, fans, office sockets and the router on a separate inverter circuit from day one. | E-101, E-102
Electrical | AC drain pipe dripping down the wall and sleeves forgotten. | Fit a 65 mm sleeve sloping out, a drain to a gully, and ODU brackets on shaded walls. | E-102
Electrical | No spare conduits for solar PV, CCTV, the sump pump and gate. | Run empty 25 mm conduits to the DB now; it costs little at this stage. | E-102, A-106
Plumbing and water | Pipes buried under the floor slab: leaks can't be found without breaking tiles. | Run supply lines along the outside walls in clamps or shallow chases, with a valve per room. | P-101
Plumbing and water | Overhead tank on a short stand: showers barely run. | Put the tank on an 18 ft stand (about 9 ft of head over the shower roses) and add a small pressure pump for the showers. | A-202, A-101
Plumbing and water | All waste going into the septic tank, which overloads it. | Keep soil and grey water separate: soil to the septic, grey to a soak trench, with inspection chambers at every bend. | P-101
Plumbing and water | Drinking borewell water without testing it (fluoride is common around Guntur). | Test the water; RO at the kitchen for drinking, and a softener if hardness exceeds 300 mg/l. | P-101
Plumbing and water | Sump lid at ground level: surface water and insects get in. | Raise the sump cover 6 in above the paving with a locked, sealed lid, and keep it 20 ft+ from the septic. | A-101
Outside: yard, gate and garden | Gate swinging out onto the road, or too narrow for two-wheelers. | Use a 7 ft gate swinging inward or sliding, with the meter and bell in the pillar. | A-101
Outside: yard, gate and garden | Two-wheeler bay with no slope: puddles. | Pave it sloping 1:50 toward the road drain. | A-101
Outside: yard, gate and garden | No outdoor drying space. | A fold-away clothesline in the south walkway beside the open wet area (sunny, private). | A-103
Note on E1: Mark Agreed / Changed / Not needed after reviewing with your architect.

## Hold_Points
# | Stage | Check before it is covered up | Who signs off | Date checked | Photos / notes
1 | Before design freeze | Soil test report, level survey of plot and road, water quality test (TDS, hardness, fluoride) | Owner, engineer
2 | Excavation | Footing depth and bearing layer seen in the pit; no black soil left under footings | Structural engineer
3 | Before each concrete pour | Reinforcement, cover blocks, laps and column positions checked; photos taken | Engineer / site supervisor
4 | Plinth | Anti-termite treatment (certificate), fill compaction, DPC laid and cured | Supervisor
5 | Before plaster | Conduits, pipes, AC sleeves, mesh over AAC joints; photos with a tape measure in view | Owner, supervisor
6 | Wet rooms | Waterproofing coats, upturns, 48 h flood test passed before any tile is laid | Owner, plumber
7 | Roof | Truss holding-down bolts, membrane and insulation, edge tiles clipped, flashings at the ventilator and valleys | Engineer, owner
8 | Before handover | Water test on every floor slope and sill, plumbing pressure test, electrical insulation and earth test | Owner, MEP

## Open_Issues
# | Category | Issue | Who resolves | Status
1 | Land | Front yard is now 8 ft (house 62 ft long): confirm the front setback allowed for this plot and road width before finalising; fall back to a 60 ft house if 10 ft is required | Architect | Open
2 | Layout | TV on Bedroom 2's east wall facing the dining bay: confirm screen size (55-65 in at about 9 ft) and a concealed HDMI/data conduit from the unit | Owner | Open
3 | Land | Agricultural land: confirm conversion to non-agricultural use with the gram panchayat / collector (AP repealed the NALA Act in 2025; new process to be confirmed) | Owner / surveyor | Open
4 | Land | Building permission route (panchayat vs DTCP / APCRDA via APDPMS) and setbacks under AP Building Rules 2017 | Architect | Open
5 | Land | Plot 27 ft x 75 ft (length to confirm by survey): north wall is 2 ft from the plot line and eaves overhang the owned north strip; septic and soak trench sit in the strip | Architect | Open
6 | Soil | Soil test (bore holes to 3 m min): black cotton soil is common in Guntur. Foundation type (isolated footings below active zone, under-reamed piles, or soil replacement) depends on it | Structural engineer | Open
7 | Structure | RCC frame with AAC infill: columns, plinth beam, lintel band, ring beam; steel truss with cyclone tie-downs | Structural engineer | Open
8 | Security | Wet area is open to the walkway: lockable steel/WPC kitchen-to-wet-area door, compound wall and gate at the back; optional MS grille shutter across the wet area opening | Owner / architect | Open
9 | Services | Groundwater: test TDS, hardness, fluoride. Plan RO for drinking and a softener for bathrooms if hardness is high | Plumber / owner | Open
10 | Services | Septic tank size and soak trench length (percolation test); keep soak trenches and gardens 6 ft+ from foundations in expansive soil | Engineer | Open
11 | Services | Electrical load (with ACs), service connection size, earthing, inverter / solar PV | Electrical engineer | Open
12 | Phase 2 | Phase 2 on the north strip will block north light and sits on the septic: plan the split now | Architect | Deferred by owner
13 | Vastu | Bed head east (master), NW ensuite, Bedroom 2's attached bath in its north-west corner on the north wall (north-west of the plot centre), common bath south of the plot centre beside the wet area (outside the central zone), dining at the plot centre, pooja in the living's south-east corner back to back with the kitchen, opening west (devotees face east), shoe cupboard between the pooja and the main door (behind the pooja's solid north wall), DB on the dining face of Bedroom 2's east wall | Vastu consultant | To confirm
14 | Climate | Roof heat: insulation, ventilated attic, ventilator lantern louvres and shutters; ODU positions on shaded walls | Architect | Open
15 | Levels | Survey road and field levels; plinth at 2 ft above finished ground (raise if site floods) | Surveyor / architect | Open

## Decisions
# | Decision (agreed in concept stage)
1 | Site is in Guntur, Andhra Pradesh (farm land), not Kerala; Kerala style kept, construction adapted to local climate and soil.
2 | Plot 27 ft x 75 ft (5 ft longer than first assumed; confirm by survey), road on east; house 62 ft x 22 ft (lengthened 2 ft for Bedroom 2) with an 8 ft front yard and 5 ft rear garden; owner accepts local practice on side setbacks (to be checked).
3 | RCC frame with AAC block walls: 9 in outer, 5 in inner, 7 in where plumbing is concealed.
4 | Plinth 2 ft above finished ground; poomukham 6 in lower; bathrooms 12 mm lower with no raised threshold.
5 | AC provisions (points, sleeves, drain, outdoor-unit brackets) in both bedrooms, the office and living; passive cooling first.
6 | Flat insulated false ceilings in bedrooms, offices, baths and kitchen; sloped ceilings in living, dining and verandah.
7 | No glass skylight: the dining gets borrowed daylight from the living, the nook window and the hall; a louvred ventilator lantern above it lets hot air out (no glass, so no greenhouse heat).
8 | Courtyard removed; the dining hall at plot centre keeps the Brahmasthan open, with the ventilator above.
9 | Single storey, no internal stair; roof access by fixed ladder; water tank on stand in SW rear garden.
10 | Service band on south (heat buffer); bedrooms and living get north light.
11 | Kitchen in SE; stove on east wall; open wet area onto the walkway; provisions in bench drawers, kitchen cabinets and lofts (no separate store).
12 | Bedroom doors widened to 3 ft; bathroom, office and store doors 2 ft 6 in.
13 | Twentieth review: Bedroom 2's bed moves to the east wall, head east, leaving an 8 x 14 ft open floor from the door to the bath and window; wardrobe to the west wall (sound buffer to the master), work table north of the bed, AC on the bath's outer wall; dresser dropped (mirror on the wardrobe).
14 | Nineteenth review: with Bedroom 2 at 17 ft, its bed turns head-south in the middle of the room (2 ft+ on both sides, under the jali); Bath 2 grows to 7' x 7' (6'-7" x 6'-4" clear) with a 3' x 3'-6" wet zone, basin in the dry zone and the door on its east wall; a dresser takes the west wall; work table and wardrobe stay on the east wall.
15 | Eighteenth review: house lengthened 2 ft to 62 ft, all of it added to Bedroom 2 (now 17 ft wide; the sitting area below it also gains 2 ft); front yard 10 ft to 8 ft (check the front setback). Bedroom 2 window back to 6 ft.
16 | Seventeenth review: sitting area gets a 5 ft tall storage cupboard on the south wall between the bench and the window; the hand-wash basin moves to the east end of the serving counter, just outside the common bath, for washing up after meals.
17 | Sixteenth review (independent Indian-architect review): Bath 2 re-planned 7' x 6' so Bedroom 2's bed (head west) has 1'-6" on both sides, work table to the east wall. Kitchen entered only from the dining-side door (hinged, 3 ft); the north sliding door is walled up so the pooja front is quiet, and a tall pantry takes the north wall. East kitchen window cut to 2 ft so the hob and chimney sit on solid wall. Septic tank moved 6 ft+ from the house and the soak pit replaced by a soak trench. Ensuite door opens outward; common bath WC side clearance 17 in, door rehung at the north jamb with a closer, geyser and shower off the window. DB moved to the dining face of Bedroom 2's east wall.
18 | Fifteenth review: TV moves to Bedroom 2's east wall facing the dining bay (the bay becomes the TV lounge; sofa faces west, living AC above the TV). Master bed moves 3'-10" south toward the bay, freeing a 9 x 7 ft zone by the north window and ensuite door with a window seat. Bedroom 2's door moves to the east end of its south wall. Bath 2's door moves to its east wall (basin to its south wall) so Bedroom 2's bed sits in the strip between the bath and the sitting area, head west on the master wall, leaving the middle of the room open.
19 | Fourteenth review (designer review): Bath 2 moves into Bedroom 2's own north-west corner, made 5'-6" x 7'-6" (about 5'-0" x 6'-11" clear) for a 3' x 3'-6" wet zone and a WC with 15 in each side and the master gets back its full room, bed position and 6 ft window. Bath doors open outward (common bath door moved to the sitting-area side, off the dining). Pooja moves 3'-6" south, back to back with the kitchen, with doors opening inward; the fridge moves into the kitchen; a shoe cupboard takes the freed wall beside the main door. Second kitchen door (sliding) straight to the dining. Bedroom 2's south-east corner is notched 1' x 1'-6" so the way from the dining into the sitting area is about 4'-2" instead of 3'-3"; Bedroom 2 gets a real queen bed, a 6 ft window and a high jali vent to the sitting area. Handrail at the entrance steps, grab bars in the baths.
20 | Common bath widened to 6'-6" x 6' (about 6'-0" x 5'-5" clear: 3 x 3 ft shower, WC and basin on the wet wall) by taking 1'-6" from the east end of the sitting area; serving counter now 6 ft.
21 | Twelfth review: Bath 2 becomes a common bath in the old pooja bay beside the wet area (5 x 6 ft, door from the sitting area, WC and basin on the shared wet wall, drains straight to the south walkway); Bedroom 2 is a clean room with no attached bath; wet area narrowed to 5 ft. Hall kept on the south so bedrooms keep their north windows.
22 | Eleventh review: the corner between the pooja and the kitchen becomes part of the kitchen and holds the fridge; the kitchen entrance moves from the dining side to the north (3 ft sliding glass door from the living); the old fridge spot extends the south counter.
23 | Tenth review: main door moved to the north end of the east wall and the pooja 3'-6" north with it, freeing the living's south-east corner beside the kitchen; verandah steps, pillars and swing realigned to the door; TV taken off the east wall (new position open).
24 | Ninth review: pooja moved to the east side, in the living's south-east corner beside the main door and back to back with the kitchen (4 x 4 ft, opens west, idols face west, family faces east). Main door moved 2'-4" north and the TV unit trimmed to suit; the old pooja bay joins the sitting area.
25 | Eighth review: plot 5 ft longer, so the house grows to 60 ft. The master stays 9'-6" x 14' (bay 7 x 8 ft, full-width wardrobe, light from the workstation window; the bay's own south window dropped). Bedroom 2 grows to 15 ft wide, the sitting area to 20 x 7'-6" (Bedroom 2 gives up 1'-6" of depth, now 15 x 14'-6") and the dining to 11 ft; the plot centre now falls in the dining, west of the ventilator (Vastu to confirm).
26 | Seventh review: Bedroom 2 enlarged to 12 x 16 ft by taking the hall strip; its door opens from the sitting area (as the master suite does); hand-wash basin back at the west end of the serving counter.
27 | Sixth review: Office 2 walls and sliding door left out for now (open workstation in the master suite, walls can be added later); Bedroom 2 becomes a study-guest room: work table with monitor beside the bath, sofa-cum-bed instead of a queen bed.
28 | Office 1 removed after family review: one office (Office 2) inside the master suite; Bedroom 2 has its own work desk.
29 | Common bathroom moved to the north side (old pooja spot), entered from the dining corner next to the hall.
30 | Second family review: store (8 x 8 ft) moved next to the bedrooms; pooja reduced to a small shrine opening onto the hall (idols face east); wet area moved west (9 x 8 ft); kitchen 14 x 10 ft with a 5 ft sliding entry from the living; dining gains a basin and crockery nook with a south window; TV moved to the living room's east wall.
31 | Pooja moved beside the wet area and opened to the west (idols face west, the family sits in the nook facing east); shared wall kept dry with no pipes, pooja floor 3 in higher; basin nook shifted west.
32 | Fifth review: Bedroom 2 made one 12 x 12 ft rectangle with a rectangular private bath (north-west corner, outer wall) and its wardrobe on the east wall; the leftover corner at the hall's west end is an open hand-wash corner; serving counter now 9 ft without a basin.
33 | Fourth review: Bath 2 made Bedroom 2's private bath (no common toilet); master suite entered through its bay from the sitting area; the old Bath 2 spot opens to the dining with a north window; family store merged back into the master bedroom as a wardrobe bay; inverter under the sitting-area bench.
34 | Earlier: walk-in wardrobe turned into a family store with a lockable door from the sitting area (inverter inside); built-in sliding wardrobes in the dressing alcove and on the master bedroom's south wall.
35 | Store wall removed: the strip from the walk-in to the pooja is one open sitting and serving area with a storage bench; hand-wash basin set into the west end of the serving counter, about 8 ft from the pooja, draining straight out to the south walkway.
36 | Wet area reduced to 6 x 6 ft and left open on its south side to the walkway (service route from the kitchen to the back of the house); kitchen door moved to face the dining (3 ft sliding glass); basin nook widened to 8 ft with a 6 ft serving counter.
37 | Main door moved to the south part of the living's east wall (still north of the house's centre line); TV on the north part of that wall; steps, swing and arugu seats rearranged on the poomukham.
38 | Third review: hall widened to about 6 ft clear (store, pooja and basin nook made 6 ft deep) so the family can sit facing the pooja; store left open to the hall for now (a wall and door can be added later); broom closet dropped, tall utility cupboard in the wet area instead.
39 | Earlier: hall widened to 4 ft clear (Bedroom 2 gives up 6 in); vents above the office, walk-in, store, pooja and kitchen doors; none at bedrooms or bathrooms (sound privacy).
40 | Ensuite widened by 1'-6" into the master (about 6'-0" x 7'-4" clear); dressing widened by the same strip; master now 9'-6" x 14'-0".
41 | Roof: Mangalore clay tiles on steel truss over insulated cement-fibre deck; all edge tiles mechanically fixed.